## Slide 1: WP2 – Biomarkers binding and quantitative analysis
Makis Angelakeris, AUTh,
agelaker@auth.gr, http://users.auth.gr/agelaker
“Graphene Bio-Platform for point-of-care early detection and monitoring of Alzheimer’s Disease”

## Slide 2: Outline
Objectives
Contacts
Deliverables & Milestones
Contacts
Timeline
Tasks
  Task 2.1
  Task 2.2
  Task 2.3
  Task 2.4
Partner | PMs
UP | 2
Q-PLAN | 0
ICN2 | 10
GRAPHEAL | 0
AUTH | 24
NOVA | 10
UEF | 0
GAADRD | 0
EVNIA | 0
ZI | 0
CeADAR | 12

## Slide 3: Objectives
Identification, synthesis, functionalization, and optimization of DNA aptamers for AD protein biomarkers.
Identification, synthesis, characterization, and evaluation of MNPs as carriers and enablers.
Conjugation of aptamers, MNPs, and Biomarkers with AD protein biomarkers.
Evaluation and validation of individual and conjugated components.

## Slide 4
Task 2.4
Tasks 2.1, 2.2
Task 2.3
NatasaPantazaki
AUTh
natasa@chem.auth.gr
Contacts
Cristian Bosch Serrano
CeADAR
cristian.boschserrano@ucd.ie
Jean-Jacques TOULMÉ
NOVAptech
jj.toulme@novaptech.com
Ruslan Alvarez
ICN2
ruslan.alvarez@icn2.cat
Aris Bakandritsos
UP
a.bakandritsos@upol.cz
Makis Angelakeris
AUTh
agelaker@auth.gr
Zoom Meetings 2/month

## Slide 5
D2.1 Conjugated MNPs/Aptamers Design, Synthesis, and Selection, Version 1 (12 months, OTHER, SEN – Sensitive, 5 – AUTH)
D2.2 Conjugated MNPs/Aptamers Design, Synthesis, and Selection, Version 2 (12 months, OTHER, SEN – Sensitive, 5 –AUTH)
D2.3 Conjugated MNPs/Aptamers Binding to AD Biomarkers evaluation, Version 1 (18 months, R — Document, report PU - Public, 5 –AUTH)
D2.4 Conjugated MNPs/Aptamers Binding to AD Biomarkers evaluation, Version 2 (30 months, R — Document, report PU - Public, 5 –AUTH)
Deliverables

## Slide 6
Milestones
2 | System Architecture and Use Cases Available | WP1 | M9 | D1.2 v1 Available
3 | Clinical Pilot Studies Protocols available and approved | WP5 | M12 | D5.1 Available
4 | First prototype of (i) conjugated MNPs/Aptamers and (ii) functionalised graphenes conjugated with ssDNA | WP2, WP3 | M18 | D2.2 v1, D3.1 v1 Available
5 | Final System Architecture, Final Pilot Studies designs, and First 2D-BioPAD prototype device Available | WP1-WP5 | M24 | D2.1 v2, D3.2 v1, D4.2 v1, D5.1 v2 Available
7 | Second prototype of (i) conjugated MNPs/Aptamers and (ii) functionalised graphenes conjugated with ssDNA. Preliminary Retrospective Study Results Available | WP3, WP5 | M30 | D2.2 v2, D3.1 v2, D5.2 v1 Available
8 | First complete 2D-BioPAD system prototype available, Enrolment of patients of the prospective | WP4 | M36 | D3.2 v2, D3.3, D4.1, D4.2 v2 Available

## Slide 7
M12:Sep2025
D2.1 v1
M18:Mar2026
D2.2 v1
M24: Sep2026
D2.1 v2
M30:Mar2027
D2.2 v2
TimeLine
WP2
M4: Jan2025
D2.1
Conjugated MNPs/Aptamers
D2.2 +Binding to AD

## Slide 8
Task 2.1: Identification, synthesis, and evaluation of Aptamers for AD protein biomarkers
  (M4-M24) [Leader: NOVA, support: AUTH, CeADAR]
Task 2.2: Optimization and functionalization of aptamers
(M13-M24) [Leader: NOVA, support: AUTH, CeADAR]
Task 2.3: Synthesis and characterization of magnetic nanoparticles as carriers and enablers
(M4-M24) [Leader: AUTH, support: NOVA]
Task 2.4: Immobilization, Functionalization & Evaluation of Conjugated MNPs/Aptamers/Biomarkers
(M18-M30) [Leader: AUTH, support: UP, ICN2, NOVA]
Tasks

## Slide 9: Task 2. 1: Identification, synthesis, and evaluation of Aptamers for AD protein biomarkers
Duration: M4-M24
Lead: NOVA, support: AUTH, CeADAR
Graphene Bio-Platform for point-of-care early detection and monitoring of Alzheimer’s Disease

## Slide 10
Identification of aptamers for AD protein biomarkers (indicatively Aβ1-40, Aβ1-42, tau181, tau217 tau231, NFL, GFAP) through a literature review and search in databases for all the available sequences of DNA aptamers.
Comparative study of their characteristics together with binding and evaluation techniques proposed.
Synthesis of up to 5 DNA aptamers per target, with the most robust properties and evaluation for their binding properties and specificity of chosen aptamers.
The evolution of the pools will be monitored by NGS sequencing (Next Generation Sequencing), and the sequences analysed with a proprietary algorithm. Candidates chosen on the basis of the bioinformatics analysis will be chemically synthesized and their binding to proteins characterized by SPR or BLI (detection of biomolecular interactions in real-time).
Task 2. 1: Identification, synthesis, and evaluation of Aptamers for AD protein biomarkers

## Slide 11: Task 2.2: Optimization and functionalization of aptamers
Duration: M13-M24
Lead: NOVA, support: AUTH, CeADAR]
Graphene Bio-Platform for point-of-care early detection and monitoring of Alzheimer’s Disease

## Slide 12
DNA aptamer length affects its immobilization and cost. Specifically, the longer the aptamer, the lower the immobilization effectiveness might be.
Evaluation and optimization of aptamers’ size. Truncated variants of aptamers will be designed on the basis of their predicted secondary structure, chemically synthesised, and studied with respect to their binding properties (SPR or BLI).
Aptamers corresponding to the minimal oligonucleotide displaying the properties of the parent aptamer will be further elaborated while one of the 2 fixed flanks of the full-length aptamer may serve for immobilization purposes on MNPs. Such modified aptamers will be evaluated via SPR or BLI protocol.
These binding properties will be used as features to, along with the structure, train a deep learning model aiding length optimization.
Task 2.2: Optimization and functionalization of aptamers

## Slide 13: Task 2.3- Synthesis and characterization of magnetic nanoparticles as carriers and enablers
Duration: M4-M24 Lead: AUTh, Support: NOVA
Graphene Bio-Platform for point-of-care early detection and monitoring of Alzheimer’s Disease

## Slide 14
Synthesis of Magnetite (Fe3O4) MNPs of different sizes
Characterization structurally, morphologically, and magnetically (TEM, XRD, VSM)
The size of the MNPs is directly reflected to their magnetic response and in turn their interaction with external magnetic fields while may affect specifically and selectively the aptamer immobilization to be held in T2.3).
Task 2.3- Synthesis and characterization of magnetic nanoparticles as carriers and enablers
            Magnetite MNPs hybrid systems (Janus MNPs) composed of a gold contact on one side and a magnetic part on the other to obtain electrical conductivity (electrochemical sensing ).
These hybrid MNPs will be conjugated with the aptamers (1↔1) following established protocols and finally purified to be used within the platform.

## Slide 15: Task 2.4-Immobilization, Functionalization and Evaluation of Conjugated MNPs/Aptamers/Biomarkers
Duration: M18-M30 Lead: AUTh Support: UP, ICN2, NOVA

## Slide 16: T2.4 Immobilization, Functionalization and Evaluation of Conjugated MNPs/Aptamers/Biomarkers
Immobilization of Aptamers on MNPs
  Aptamers immobilization protocols will be tested to optimize their immobilization efficiency on MNPs depending on the size of the MNP and of the aptamers.
Functionalization of Conjugated MNPs/Aptamers /Biomarkers
  Various conditions will be applied to optimize the rate of MNPs-Aptamers/biomarkers. This work will be multiplied by the number of biomarkers of our interest. ELISA and electrophoresis methods will be used to quantified conjugated and non conjugated biomarkers and aptamers.
Evaluation of Conjugated MNPs/Aptamers / Biomarkers
  A systematic investigation of the binding capacity of conjugated MNPs/Aptamers with the selected biomarkers in simple and complex solutions (artificial CSF and plasma) will be performed.

## Slide 17
D2.1 | Conjugated MNPs/Aptamers Design, Synthesis, and Selection | Selection of specimens based on evaluation of (v1) immobilization data and (v2) binding capacity of the aptamers with specific biomarkers.
D2.2 | Conjugated MNPs/Aptamers Binding to AD Biomarkers evaluation | Evaluation results of the binding affinity and specificity (v1) to AD biomarkers after optimised functionalisation (v2).
Deliverables

## Slide 18: Interdependencies with other WPs/Tasks
T3.1 | Functionalized graphene synthesis and ssDNA conjugation | Functionalized graphene synthesis and ssDNA conjugation | UP
T3.2 | Fabrication and testing of Graphene-based biosensors | Fabrication and testing procedures for both the electrochemical and GFET biosensing strategies | ICN2
T3.3 | AI for 2DM-based PoC IVD Design | AI-based solution and data for the improvement of the graphene-based designs including generated | CeADAR
T1.1 | MCI to AD Biomarker Deep Dive Analysis for Early Diagnosis | Detailed mapping of End-users’ Needs, Disease Challenges, and Requirements | Q-PLAN
T1.2 | System Architecture | High-level system architecture and evaluation use cases design | ICN2
WP1
WP3
WP2

## Slide 19: Issues to discuss-Critical Points
Task2.1 Which aptamers & which biomarkers?
Task2.2 Selection rules & Validation
Task2.3 MNPs immobilization with aptamers
Task 2.4 Evaluation of MNPs/aptamers/biomarkers

## Slide 20: Thank you for your attention! WP2
Makis Angelakeris, AUTh,
agelaker@auth.gr, http://users.auth.gr/agelaker
WP2 – Biomarkers binding and quantitative analysis
“Graphene Bio-Platform for point-of-care early detection and monitoring of Alzheimer’s Disease”