## Action List
Latest update: 05.11.2024
AP# | Action Point | Partner | Deadline | Status | Comments
2.1.1 | Identify the sequence for the p-tau217 peptide | NOVA / AUTH / UP-CATRIN | 2024-10-31 | Done
2.1.2 | Identification of the aptamers’ binding site(s), through simulations. | UP-CATRIN | TBD | Pending | Too challenging task to simulate
2.1.3 | Share w/ CeADAR training data for binding location of proteins other than thrombin | NOVA | 2024-11-29 | Pending
2.1.4 | AI/ML model for binding site identification | CeADAR | 2024-12-20 | Pending | Start with open available data from Thrombin (and other known proteins)
2.1.5 | Meeting with the University of Cyprus to discuss availability / procurement of Aβ and p-tau peptides | UP-CATRIN / NOVA | 2024-11-06 | Ongoing
2.1.6 | Visit Shanghai company to discuss provision of p-tau 217 and Αβ proteins | GRAPHEAL | 2024-11-15 | Pending | The Shanghai company offered to send some p-tau 217 samples for free.
2.1.7 | Provide feedback to the consortium from visit to Shanghai company for p-tau protein peptides and full protein | GRAPHEAL | 2024-11-22 | Pending
2.1.8 | Follow up with the University of Wurzburg (Dr. Maric) for p-tau and Aβ | NOVA | 2024-11-08 | Ongoing
2.1.9 | Communicate with other companies offering p-tau 217 (Sinobio, Biolegend, etc.). | GRAPHEAL / NOVA / AUTH/ ICN2 | 2024-11-08 | Pending
2.1.10 | Provide the truncated/optimized aptamer sequences for GFAP | NOVA | 2024-11-22 | Pending
2.1.11 | Contact SIAB to get insight on the procurement form for Aβ | NOVA / AUTH | 2024-11-29 | Pending | TBC
2.1.12 | Finalise the selection of aptamers for NfL | NOVA | 2024-11-29 | Ongoing
2.1.13 | MNP conjugation with Thrombin aptamer | AUTH | 2024-11-29 | Ongoing
2.1.14 | Initiate Selection for p-tau217 | NOVA | November / December 2024 | Pending | Depending on availability of peptides
2.1.15 | Initiate Selection for Aβ40 | NOVA | November / December 2024 | Pending | Depending on availability of peptides
2.1.16 | Initiate Selection for Aβ42 | NOVA | November / December 2024 | Pending | Depending on availability of peptides
2.1.17 | Provide the truncated/optimized aptamer sequences for NfL | NOVA | 2024-12-20 | Pending | (Assuming 3 weeks from previous step)
2.1.18 | Decision on mitigation plan for targeted biomarkers | All partners | 2025-02-04 | Pending | Current biomarkers
2.1.19 | First draft of D2.3 for Quality Review | AUTH | 2024-02-28 | Pending | Αβ40, Αβ42, p-tau217, GFAP, and NfL
2.1.20 | Quality Review available | GRAPHEAL, ZI | 2024-03-14 | Pending | (p-tau181 backup)
2.1.21 | Final version of D2.3 available for submission | AUTH | 2024-03-30 | Pending
2.3.1 | MNP conjugation with Thrombin to have a successful result of conjugation of MNPs with Thrombin by M18 | AUTH | 2025-01-31 | Pending
2.3.2 | Evaluate MNP conjugation with truncated GFAP aptamer | AUTH | 2025-01-31 | Pending
3.1.1 | Purchase of the GFAP aptamer and protein and the NfL antibody and protein for GFET biosensing | UP-CATRIN | 2024-11-15 | Ongoing | To be sent to GRAPHEAL directly
3.1.2 | Purchase of Αβ40 & Αβ41 antibodies and proteins for experimentation and testing- electrochemical biosensing | ICN2 | 2024-11-15 | Pending
3.1.3 | Purchase of GFAP truncated aptamer for electrochemical biosensing | ICN2 | 2024-12-13 | Pending
3.1.4 | Graphene derivatives' SYNTHESIS for the electrochemical biosensor | UP-CATRIN | 2024-11-29 | Ongoing
3.1.5 | Send Graphene derivatives to ICN2 to plan integration in the device | UP-CATRIN | 2024-11-29 | Pending
3.3.1 | Provide a list of data generated (type, format, volume) during the design, synthesis and characterization of graphene-based prototypes | UP-CATRIN, ICN2, and GRAPHEAL | 2024-11-29 | Ongoing | To support CeADAR’s work
3.3.2 | Preliminary results on GFAP with GFET biosensor | GRAPHEAL | 2024-12-20 | Pending
3.3.3 | Evaluate the conjugated MNPs- aptamers sent by AUTH | ICN2 | 2024-12-20 | Pending
3.3.4 | Confirm Biosafety Level 2 clearance | ICN2 & GRAPHEAL | 2024-12-20 | Pending
3.3.5 | Work on dual functionalisation of graphene for the electrochemical biosensor | UP-CATRIN | 2024-12-20 | Pending
3.3.6 | Preliminary results on GFAP with electrochemical biosensor | ICN2 | 2025-02-28 | Ongoing | Truncated version
3.3.7 | Preliminary results on NfL with GFET biosensor | GRAPHEAL | 2025-01-31 | Pending
3.3.8 | Meeting for data/ evidence of the device towards regulatory compliance. Identify data to collect during the implementation of the device (sensitivity, specificity etc.). | EVNIA/ ICN2 / GRAPHEAL | 2024-11-29 | Pending
3.3.9 | First draft of D3.1 for Quality Review | UP-CATRIN | 2024-02-28 | Pending
3.3.10 | D3.1 Quality Review | NOVA, CeADAR | 2024-03-14 | Pending
3.3.11 | Final version of D3.1 available for submission | UP-CATRIN | 2024-03-30 | Pending
3.4.1 | Work on GFAP towards the sensor development | GRAPHEAL | 2024-12-20 | Pending
3.4.2 | Evaluate the MNPs from AUTH to amplify signal | GRAPHEAL | 2025-01-31 | Pending
4.2.1 | Organise meeting to identify contribution/collaboration | GRAPHEAL | 2024-11-15 | Ongoing
4.2.2 | Firmware development for the 2D-BioPAD decision support tool | GRAPHEAL | 2024-12-20 | Pending
4.2.3 | App Mock-ups available for the 2D-BioPAD decision support tool | GRAPHEAL | 2025-01-31 | Pending
5.1.1 | Submit the prospective clinical study documents for ethical approval | ZI | 2024-10-31 | Pending | What is the status? Submitted or not?
5.1.2 | Inform about approval status for both the retrospective and prospective clinical pilot study documents | ZI | 2024-12-20 | Pending
5.1.3 | Meeting about the regulatory aspects of the clinical protocol | EVNIA / UEF | 2024-11-29 | Pending | Support for reaching out to FIMEA – no need to prepare a regulatory compliant protocol (yet)
5.1.4 | Materials and Data Transfer agreement template | UEF | 2024-12-20 | Ongoing | To be shared with GAADRD, ZI, ICN2 & GRAPHEAL
5.1.5 | Finalise the Materials and Data Transfer agreement template | UEF, GAADRD, ZI, ICN2 & GRAPHEAL | 2025-01-29 | Pending
5.1.6 | Arrange a meeting with the Finnish medicine agency to discuss the regulatory-compliant clinical study protocol | UEF / EVNIA | 2024-12-20 | Pending
5.1.7 | Share the Protocol with members of the SIAB for comments | UEF / GAADRD | 2025-03-14 | Pending | In whatever status the protocol is
6.1.1 | Promo articles | Q-PLAN, NOVA, CeADAR | 2024-11-30 | Ongoing | Aptamer Article pending NOVA’s approval. Q-PLAN to share draft to CeADAR
6.1.2 | Social media campaigns - partners asked to interact (re-post, share, comment) | Q-PLAN / Support by all | Ongoing | Ongoing
6.1.3 | Website content update with educational material | Q-PLAN / Support by all | Ongoing | Ongoing
6.1.4 | Press Releases for GW24 & 3rd PM | Q-PLAN | 2024-11-08 | Pending
6.1.5 | GW24 Video Interview from ICN2 | Q-PLAN / ICN2 | 2024-12-20 | Pending
6.2.1 | Organise interviews for discussing exploitation pathways | Q-PLAN / ALL | 2024-11-15 | Pending | Nov24 – Feb 25
6.2.2 | Update the exploitation plan | Q-PLAN | 2025-03-30 | Pending
6.3.1 | Initiate market analysis in the context to T6.3 | Q-PLAN | 2024-10-10 | Ongoing
6.3.2 | Organise interviews for discussing market analysis and business with a key stakeholder from each partner | Q-PLAN / ALL | 2024-11-30 | Ongoing
6.3.3 | Finalise interviews for market analysis, with selected interviewees | Q-PLAN | 2025-02-28 | Pending
6.3.4 | Aggregated results from the market analysis | Q-PLAN | 2025-03-30 | Pending
6.3.5 | Present results to 4th Project Meeting | Q-PLAN | March-April 2025 | Pending
6.4.1/6.5.1 | Regulatory Workshop / Webinar | EVNIA / Q-PLAN | February 2025 | Pending
6.5.2 | Explore synergies with GRAPHERGIA | Q-PLAN / UP-CATRIN | 2024-11-30 | Pending | Communication initiated.
6.5.2 | Explore synergies with SAFARI | Q-PLAN / UP-CATRIN | 2024-11-30 | Pending
6.5.3 | Explore synergies with GIANCE | Q-PLAN / UP-CATRIN | 2024-11-30 | Pending | Communication initiated.
6.5.4 | Explore synergies with 2D-PL | Q-PLAN / UP-CATRIN | 2024-11-30 | Pending
6.5.5 | Explore workshop with PPs/Ams | Q-PLAN / UP-CATRIN | 2024-11-29 | Pending | To be discussed during the GF D&C meeting on the 14th of November
6.5.6 | Organise Webinar on Clinical Applications of Graphene-based solutions | UEF / Q-PLAN | 2024-12-20 | Pending | Identify theme and speakers (webinar for April 2025)
6.5.7 | Organise Webinar on AI for 2D Material Science, within GF | CeADAR / Q-PLAN |  | Pending | Identify theme and speakers (webinar for Jun/Jul 2025)
6.5.8 | Initiate collaboration with MUNASET on market analysis, etc. | Q-PLAN | Jan/Feb 2025 | Pending
7.1.1 | Partners update KPIs list here | Q-PLAN | 2024-11-04 | Pending
7.1.2 | Partners update KPIs requested by the GFI here | Q-PLAN/ ALL | 2024-11-04 | Pending
7.3.1 | Align with the Clinical Pilot Study Protocol | Q-PLAN / UEF / EVNIA | April 2025 | Pending
7.3.2 | Align with D5.1 sensitive data collection procedures & D1.1 ethics roadmap, for the app development | GRAPHEAL / ICN2 | April 2025 | Pending
7.4.1 | Partners provide input on 1st & 2nd Semester internal progress report | ALL | 2024-10-25 | Delay | GRAPHEAL, ZI pending
7.4.2 | Semester internal reporting finalise | Q-PLAN/ ALL | 2024-11-15 | Pending | Fine-tuning
7.4.3 | Financial report -partners' fill template & send to UP | ALL | 2024-10-31 | Delay
7.4.4 | Q-PLAN shares the 3rd project meeting minutes with partners | UP-CATRIN / Q-PLAN | 2024-11-01 | Done
7.4.5 | Partners provide feedback to the meeting minutes | ALL | 2024-11-04 | Ongoing
7.4.6 | Final Project Meeting minutes shared with partners | UP-CATRIN / Q-PLAN | 2024-11-08 | Pending
7.4.7 | Hold digital monthly meetings (agenda, moderation, minutes, etc.) | UP & Q-PLAN/ ALL | 2024-12-03 | Ongoing
7.4.8 | Planning for 4th Project meeting in Bordeaux (tbc) in March 2025 | NOVA/ UP-CATRIN / Q-PLAN | Nov-Dec 2024 | Pending
7.4.9 | Contact with PO for review arrangements | UP-CATRIN | Jan 2025 | Pending
7.4.10 | Initiate the 1st Period Reporting (activity reporting will be initiated a bit earlier) | UP-CATRIN, Q-PLAN / ALL | 2025-04-01 | Pending
7.4.11 | Submit report to the EC | UP-CATRIN, ALL | TBD | Pending

## Events
# | Partner | Event description (conference, meeting etc) | Description of activity (i.e. poster presentation, speech) | Date | Type of audience | Size of audience | Status (completed/ Upcoming) | Description of the objective(s) with reference to a specific project output (max 200 characters) | Comments
1 | [6 empty] | Upcoming
2 | [6 empty] | Completed
3
4
5
6
7
8
9
10
11
12

## Participants list
No | Organisation | Country | Participant
1 | UNIVERZITA PALACKEHO V OLOMOUCI (UP) | Czechia | Aristeidis Bakandritsos | Aristeidis Bakandritsos
|  |  | Lucie Hrabalikova | Lucie Hrabalikova
2 | Q-PLAN INTERNATIONAL ADVISORS PC (Q-PLAN) | Greece | - | Alexandra Gkouma
|  |  | Aristotelis Folas | Aristotelis Folas
|  |  | Apostolos Tsolakis | Apostolos Tsolakis
3 | FUNDACIO INSTITUT CATALA DE NANOCIENCIA I NANOTECNOLOGIA (ICN2) | Spain | Marianna Rossetti | Marianna Rossetti
Ronaldo Valentin Challhua Reynoso
Sebastián Acebal Colli
4 | GRAPHEAL | France | Vincent Bouchiat | Vincent Bouchiat
5 | ARISTOTELIO PANEPISTIMIO THESSALONIKIS (AUTH) | Greece | Mavroeidis Angelakeris | Mavroeidis Angelakeris
|  |  | - | Anastasia Pantazaki
|  |  | - | George Katsipis
-
|  |  | - | Antonios Makridis
|  |  | - | Eleni Tzekaki
6 | NOVAPTECH (NOVA) | France | - | Jean-Jacques Toulmé
Sandeep Kumar
7 | ITA-SUOMEN YLIOPISTO (UEF) | Finland | - | Alina Solomon
|  |  | - | Mervi Issakainen
|  |  | - | Kaisa Paldanius
8 | ELLINIKI ETAIRIA NOSOY ALZHEIMER KAI SYGGENON DIATARACHON SOMATEIO (GAADRD) | Greece | - | Magda Tsolaki
|  |  | Anthoula Tsolaki | Anthoula Tsolaki
|  |  | - | Foteini Pikouli
9 | EVNIA APS (EVNIA) | Denmark | Gitte Holst | Gitte Holst
|  |  | - | Angeliki Koukoura
|  |  | - | Vaso Basinou
|  |  | - | Kyriaki Antonopoulou
|  |  | - | Eirini Papadaki
10 | ZENTRALINSTITUT FUER SEELISCHE GESUNDHEIT (ZI) | Germany | - | Lutz Froelich
11 | UNIVERSITY COLLEGE DUBLIN, NATIONAL UNIVERSITY OF IRELAND, DUBLIN (CeADAR) | Ireland | Polat Goktas | Polat Goktas
|  |  | Cristian Bosch Serrano | Cristian Bosch Serrano

## Sheet2
Done | Completed
Pending | Upcoming
Delay
Ongoing
The Action Point Number (AP#) is the WP Number. Task Number. Index. Hence, an AP# of 4.2.13 refers to WP4, Task 4.2 and related item 13.
here