## Action List
Latest update: 03.12.2024
AP# | Action Point | Partner | Deadline | Status | Comments
2.1.1 | Share w/ CeADAR training data for binding location of proteins other than thrombin | NOVA | 2024-11-29 | Done | Shared literature on 02/12/2024
2.1.2 | AI/ML model for binding site identification (Start with open available data from Thrombin and other known proteins) | CeADAR | 2024-12-20 | Ongoing | Next step is to use the model for GFAP.
2.1.3 | Meeting with the University of Cyprus to discuss availability / procurement of Aβ and p-tau peptides | UP-CATRIN / NOVA | 2024-11-06 | Ongoing | Waiting for peptides from Cyprus
2.1.4 | Provide feedback to the consortium from visit to Shanghai company for p-tau protein peptides and full protein | GRAPHEAL | 2024-11-22 | Pending | Shanghai company can provide p-tau217 peptides and antibodies
2.1.5 | Follow up with the University of Wurzburg (Dr. Maric) for p-tau and Aβ | NOVA | 2024-12-13 | Ongoing | Did not follow up. Alternative: ongoing discussion with Univeristy of Cyprus
2.1.6 | Communicate with other companies offering p-tau 217 (Sinobio, Biolegend, etc.). | GRAPHEAL / NOVA / AUTH/ ICN2 | 2024-12-13 | Pending
2.1.7 | Provide the truncated/optimized aptamer sequences for GFAP | NOVA | 2024-11-22 | Delay | Expected to be delivered by 13th December
2.1.8 | Contact SIAB to get insight on the procurement form for Aβ | NOVA / AUTH | 2024-11-29 | Delay
2.1.9 | Finalise the selection of aptamers for NfL | NOVA | 2024-12-13 | Ongoing
2.1.10 | MNP conjugation with Thrombin aptamer | AUTH | 2024-12-13 | Ongoing
2.1.11 | Initiate Selection for p-tau217 | NOVA | December 2024 | Pending | Depending on availability of peptides- to update
2.1.12 | Initiate Selection for Aβ40 | NOVA | December 2024 | Pending | Depending on availability of peptides- to update
2.1.13 | Initiate Selection for Aβ42 | NOVA | December 2024 | Pending | Depending on availability of peptides- to update
2.1.14 | Provide the truncated/optimized aptamer sequences for NfL | NOVA | 2025-01-10 | Pending
2.1.15 | Decision on mitigation plan for targeted biomarkers: Αβ40, Αβ42, p-tau217, GFAP, and NfL. (p-tau181 backup) | All partners | 2025-02-04 | Pending
2.1.16 | First draft of D2.3 for Quality Review. | AUTH | 2024-02-28 | Pending
2.1.17 | Quality Review available | GRAPHEAL, ZI | 2024-03-14 | Pending
2.1.18 | Final version of D2.3 available for submission | AUTH | 2024-03-30 | Pending
2.3.1 | MNP conjugation with Thrombin to have a successful result of conjugation of MNPs with Thrombin by M18 | AUTH | 2025-01-31 | Ongoing | Final results by 13/12
2.3.2 | Evaluate MNP conjugation with truncated GFAP aptamer | AUTH | 2025-01-31 | Pending
3.1.1 | Purchase of the GFAP aptamer and protein and the NfL antibody and protein for GFET biosensing. To be sent to GRAPHEAL directly | UP-CATRIN | 2024-12-06 | Ongoing | Delivered to Grapheal: NfL, GFAP proteins, NfLantibody, antibody Biotin. GFAPaptamer delivery expected in December.
3.1.2 | Purchase of Αβ40 & Αβ42 antibodies and proteins for experimentation and testing- electrochemical biosensing | ICN2 | 2024-11-15 | Ongoing | What is the status of purchase?
3.1.3 | Purchase of GFAP truncated aptamer for electrochemical biosensing | ICN2 | 2024-12-13 | Pending
3.1.4 | Graphene derivatives' SYNTHESIS for the electrochemical biosensor | UP-CATRIN | 2024-12-13 | Ongoing | Synthesis of graphene derivatives functionalized with i) thiol (cysteamine), ii) carboxyl (direct carbon-carbon bond), iii) amine (1,3-diamino-2-propanol), characterization is performed, iv) ii) carboxyl (direct carbon-carbon bond) and nitrogen doping
3.1.5 | Binding of aptamers on graphene derivatives | UP-CATRIN | 2024-12-13 | Ongoing | Evaluation of electrochemical activity of graphenes and effectiveness of aptamers binding
3.3.1 | Provide a list of data generated (type, format, volume) during the design, synthesis and characterization of graphene-based prototypes. To support CeADAR’s work | UP-CATRIN, ICN2, and GRAPHEAL | 2024-12-13 | Ongoing | UP can provide structural data of graphene (XPS) to CeADAR.
3.3.2 | Preliminary results on GFAP with GFET biosensor | GRAPHEAL | 2024-12-20 | Pending
3.3.3 | Evaluate the conjugated MNPs- aptamers sent by AUTH | ICN2 | 2024-12-20 | Pending
3.3.4 | Confirm Biosafety Level 2 clearance | ICN2 & GRAPHEAL | 2024-12-20 | Pending | ICN2 & GRAPHEAL required to give final reply by the end of December.
3.3.5 | Work on dual functionalisation of graphene for the electrochemical biosensor | UP-CATRIN | 2024-12-20 | Ongoing | Synthesis of graphene derivatives functionalized with two groups i) thiol (cysteamine), and amine (1,3-diamino-2-propanol), ii) carboxyl groups and fluorine
3.3.6 | Preliminary results on truncated GFAP with electrochemical biosensor | ICN2 | 2025-02-28 | Ongoing
3.3.7 | Meeting for data/ evidence of the device towards regulatory compliance. Identify data to collect during the implementation of the device (sensitivity, specificity etc.). | EVNIA/ ICN2 / GRAPHEAL | 2024-11-29 | Done | Evnia has provided a list of Standards to guide ICN2 and GRAPHEAL in defining relevant endpoints as per device specifications. A meeting to discuss further has been suggested.
3.3.8 | First draft of D3.1 for Quality Review | UP-CATRIN | 2024-02-28 | Pending
3.3.9 | D3.1 Quality Review | NOVA, CeADAR | 2024-03-14 | Pending
3.3.10 | Final version of D3.1 available for submission | UP-CATRIN | 2024-03-30 | Pending
3.4.1 | Work on GFAP towards the sensor development | GRAPHEAL | 2024-12-20 | Pending
3.4.2 | Preliminary results on NfL with GFET biosensor | GRAPHEAL | 2025-01-31 | Pending
3.4.3 | Evaluate the MNPs from AUTH to amplify signal | GRAPHEAL | 2025-01-31 | Pending
4.2.1 | Meeting to identify contribution/collaboration | GRAPHEAL | 2024-12-02 | Ongoing
4.2.2 | Firmware development for the 2D-BioPAD decision support tool | GRAPHEAL | 2024-12-20 | Pending
4.2.3 | App Mock-ups available for the 2D-BioPAD decision support tool | GRAPHEAL | 2025-01-31 | Pending
4.2.4 | Set up a meeting of GRAPHEAL & ICN2 to discuss LFA for plasma separation on the device | ICN2 / GRAPHEAL | 2025-01-31 | Pending
4.2.5 | Clarify contribution of other partners in WP4 tasks | GRAPHEAL | 2025-01-31 | Pending
4.2.6 | Timeline for device and app development to be presented in next PM | ICN2 / GRAPHEAL | Mar 2025 | Pending
5.1.1 | Submit the prospective clinical study documents for ethical approval | ZI | 2024-10-31 | Delay | ZI submitted two different protocols for approval. One for the retrospective and one for the prospective.
5.1.2 | Inform about approval status for both the retrospective and prospective clinical pilot study documents | ZI | 2024-12-20 | Pending | The retrospective did not encounter issues, but the prospective is being “questioned” by their Ethical Committee.
5.1.3 | Meetings of WP5 partners- German protocol and regulatory aspects of the clinical protocol. Timeline for the next steps in all clinicals centres. | EVNIA / UEF | 2024-12-13 | Ongoing | Support for reaching out to FIMEA – no need to prepare a regulatory compliant protocol (yet)
5.1.4 | Materials and Data Transfer agreement template. To be shared with GAADRD, ZI, ICN2 & GRAPHEAL | UEF | 2024-12-20 | Ongoing
5.1.5 | Finalise the Materials and Data Transfer agreement template | UEF, GAADRD, ZI, ICN2 & GRAPHEAL | 2025-01-29 | Pending
5.1.6 | Arrange a meeting with the Finnish medicine agency (FIMEA) to discuss the regulatory-compliant clinical study protocol | UEF | 2024-12-20 | Pending | First discuss informally to seek advice from FIMEA. Then, discussion w/ EVNIA
5.1.7 | Share the Protocol with members of the SIAB for comments, In whatever status the protocol is | UEF / GAADRD | 2025-03-14 | Pending
5.1.8 | Check if clinical protocol needs to separate input for retrospective and prospective | EVNIA/ UEF / GAADRD / ZI | 2025-03-28 | Pending | Two devices for retrospective and one to be selected for prospective (?)
6.1.1 | Promo articles | Q-PLAN, NOVA, CeADAR | 2024-11-06 | Done
6.1.2 | Social media campaigns - partners asked to interact (re-post, share, comment) | Q-PLAN / Support by all | Ongoing | Ongoing
6.1.3 | Website content update with educational material | Q-PLAN / Support by all | Ongoing | Ongoing
6.1.4 | GW24 Video Interview from ICN2 | Q-PLAN / ICN2 | 2024-12-20 | Pending
6.2.1 | Organise interviews for discussing exploitation pathways | Q-PLAN / ALL | 2024-12-13 | Ongoing | Nov24 – Feb 25.UP & ICN2 done, AUTH and GRAPHEAL are next
6.2.2 | Update the exploitation plan | Q-PLAN | 2025-03-30 | Pending
6.3.1 | Secondary market analysis in the context to T6.3 | Q-PLAN | 2024-02-14 | Ongoing
6.3.2 | Organise interviews for discussing market analysis and business with a key stakeholder from each partner | Q-PLAN / ALL | 2024-12-13 | Ongoing | Planned with UP, ICN2. Waiting GRAPHEAL response for Jan
6.3.3 | Finalise interviews for market analysis, with selected interviewees | Q-PLAN | 2025-02-28 | Pending
6.3.4 | Aggregated results from the market analysis | Q-PLAN | 2025-03-30 | Pending
6.3.5 | Present results to 4th Project Meeting | Q-PLAN | March-April 2025 | Pending
6.4.1/6.5.1 | Regulatory Workshop / Webinar | EVNIA / Q-PLAN | 2025-02-10 | Pending | Online webinar with a combination of presentation and discussion. Webinar Title: European Regulations for MDs and IVDs - What does it require to get market access for MDs and IVDs?
6.5.1 | GIANCE synergy: to provide reply, if interested to apply LCA in the two biosensors | GRAPHEAL & ICN2 | 2024-12-13 | Pending
6.5.2 | Explore synergies with GRAPHERGIA | Q-PLAN / UP-CATRIN | 2024-12-13 | Ongoing
6.5.3 | Explore synergies with SAFARI | Q-PLAN / UP-CATRIN | 2024-12-13 | Pending
6.5.4 | Explore synergies with GIANCE | Q-PLAN / UP-CATRIN | 2024-12-13 | Ongoing
6.5.5 | Explore synergies with 2D-PL | Q-PLAN / UP-CATRIN | 2024-12-13 | Pending
6.5.6 | Explore workshop with PPs/Ams (discussed during the GF D&C meeting on the 14th of November) | Q-PLAN / UP-CATRIN | 2024-12-20 | Ongoing
6.5.7 | Organise Webinar on Clinical Applications of Graphene-based solutions (for April 2025) - Identify theme and speakers | UEF / Q-PLAN | 2024-12-20 | Pending
6.5.8 | Organise Webinar on AI for 2D Material Science, within GF (for Jun/Jul 2025)- Identify theme and speakers | CeADAR / Q-PLAN |  | Pending
6.5.9 | Initiate collaboration with MUNASET on market analysis, etc. | Q-PLAN | Jan/Feb 2025 | Pending
7.1.1 | Partners update KPIs list here | Q-PLAN | 2024-12-06 | Pending
7.1.2 | Partners update KPIs requested by the GFI here | Q-PLAN/ ALL | 2024-12-06 | Pending
7.3.1 | Align with the Clinical Pilot Study Protocol | Q-PLAN / UEF / EVNIA | April 2025 | Pending
7.3.2 | Align with D5.1 sensitive data collection procedures & D1.1 ethics roadmap, for the app development | GRAPHEAL / ICN2 | April 2025 | Pending
7.4.1 | Partners provide input on 1st & 2nd Semester internal progress report | ALL | 2024-10-25 | Done
7.4.2 | Semester internal reporting finalise | Q-PLAN/ ALL | 2024-11-15 | Done
7.4.3 | Financial report -partners' fill template & send to UP | ALL | 2024-10-31 | Delay | We are missing a financial report from Grapheal
7.4.4 | Hold digital monthly meetings (agenda, moderation, minutes, etc.) | UP & Q-PLAN/ ALL | 2024-12-03 | Ongoing
7.4.5 | Planning for 4th Project meeting in Olomouc in March 2025 | UP-CATRIN / Q-PLAN | Nov-Dec 2024 | Ongoing
7.4.6 | Contact with PO for review arrangements | UP-CATRIN | Jan 2025 | Pending
7.4.7 | Initiate the 1st Period Reporting (activity reporting will be initiated a bit earlier) | UP-CATRIN, Q-PLAN / ALL | 2025-04-01 | Pending
7.4.8 | All partners provide their input for 1st Period Reporting (Technical & Financial) | ALL | 2025-04-30 | Pending
7.4.9 | Submit report to the EC | UP-CATRIN, ALL | Mid-May 2025 | Pending

## Events
# | Partner | Event description (conference, meeting etc) | Description of activity (i.e. poster presentation, speech) | Date | Type of audience | Size of audience | Status (completed/ Upcoming) | Description of the objective(s) with reference to a specific project output (max 200 characters) | Comments
1 | [6 empty] | Upcoming
2 | [6 empty] | Completed
3
4
5
6
7
8
9
10
11
12

## Participants list
No | Organisation | Country | Participant
All people possible to attend
1 | UNIVERZITA PALACKEHO V OLOMOUCI (UP) | Czechia | Aristeidis Bakandritsos | Aristeidis Bakandritsos
|  |  | Lucie Hrabalikova | Lucie Hrabalikova
2 | Q-PLAN INTERNATIONAL ADVISORS PC (Q-PLAN) | Greece | - | Alexandra Gkouma
|  |  | Aristotelis Folas | Aristotelis Folas
|  |  | Apostolos Tsolakis | Apostolos Tsolakis
3 | FUNDACIO INSTITUT CATALA DE NANOCIENCIA I NANOTECNOLOGIA (ICN2) | Spain | Marianna Rossetti | Marianna Rossetti
Ronaldo Valentin Challhua Reynoso
Sebastián Acebal Colli
4 | GRAPHEAL | France | Vincent Bouchiat | Vincent Bouchiat
5 | ARISTOTELIO PANEPISTIMIO THESSALONIKIS (AUTH) | Greece | Mavroeidis Angelakeris | Mavroeidis Angelakeris
|  |  | - | Anastasia Pantazaki
|  |  | - | George Katsipis
-
|  |  | - | Antonios Makridis
|  |  | - | Eleni Tzekaki
6 | NOVAPTECH (NOVA) | France | - | Jean-Jacques Toulmé
Sandeep Kumar
7 | ITA-SUOMEN YLIOPISTO (UEF) | Finland | - | Alina Solomon
|  |  | - | Mervi Issakainen
|  |  | - | Kaisa Paldanius
8 | ELLINIKI ETAIRIA NOSOY ALZHEIMER KAI SYGGENON DIATARACHON SOMATEIO (GAADRD) | Greece | - | Magda Tsolaki
|  |  | Anthoula Tsolaki | Anthoula Tsolaki
|  |  | - | Foteini Pikouli
9 | EVNIA APS (EVNIA) | Denmark | Gitte Holst | Gitte Holst
|  |  | - | Angeliki Koukoura
|  |  | - | Vaso Basinou
|  |  | - | Kyriaki Antonopoulou
|  |  | - | Eirini Papadaki
10 | ZENTRALINSTITUT FUER SEELISCHE GESUNDHEIT (ZI) | Germany | - | Lutz Froelich
11 | UNIVERSITY COLLEGE DUBLIN, NATIONAL UNIVERSITY OF IRELAND, DUBLIN (CeADAR) | Ireland | Polat Goktas | Polat Goktas
|  |  | Cristian Bosch Serrano | Cristian Bosch Serrano

## Sheet2
Done | Completed
Pending | Upcoming
Delay
Ongoing
The Action Point Number (AP#) is the WP Number. Task Number. Index. Hence, an AP# of 4.2.13 refers to WP4, Task 4.2 and related item 13.
here